## Overall Plan
No. | Main Requirements | Requirements Details | EFT(Days)
Overall Plan
| Description |  | Days
1 | Dashboards |  | 11.25
2 | Reporting | Format to be provided. Estimates will be given after looking at and analysing the Reports Formats. | 0
3 | User Management |  | 12.5
4 | Inventory Management |  | 44.5
5 | Financial Documents |  | 16.25
6 | Website |  | 27
7 | Customer & Invoices |  | 10
| Total |  | 121.5

## Dashboards
Analysis & DB Design
1 | Re Analysis with Team |  | 1
2 | DB Design |  | 0.5
Dashboard Widgets
Dasboards
| Widget IRF for Employee |  | 0.75
| Widget IRF for inventory manager |  | 0.75
| Widget RIF for Employee |  | 0.75
| Widget RIF for inventory manager |  | 0.75
| Widget DIF for inventory module |  | 0.75
| Widget DIF for Employee |  | 0.75
| Widget TIR for Warehouse manager |  | 0.75
| Widget RIF for inventory manager |  | 0.75
| Widget RIF for inventory manager |  | 0.75
| Widget PO for Employee |  | 0.75
| Widget PO of inventory manager |  | 0.75
| Widget RFI for Employees |  | 0.75
| Widget RFI for inventory manager |  | 0.75
Deployment, Testing and Client Reworks
| Deployment | Current Module Deployment & Testing
Client ReWork
2nd Deployment & Testing
|  | Total | 11.25

## Reporting
Analysis & DB Design
1 | Re Analysis with Team |  | 0
2 | DB Design |  | 0
Reports
Reports
| Items report | Format to be provided. Estimates will be given after looking at and analysing the Reports Formats. | -
| RFI report |  | -
| IRF report |  | -
| RIF report |  | -
| DIF report |  | -
| TIR report |  | -
| PO report |  | -
Physical Count
Deployment, Testing and Client Reworks
| Deployment | Current Module Deployment & Testing
Client ReWork
2nd Deployment & Testing
|  | Total | 0

## User Management
No. | Main Requirements | Requirements Details | EFT(Days) | To Do
Analysis
1 | Re Analysis with Team |  | 0.5
2 | DB Design |  | 0.5
Baseline Structure for core modules
| Architecture Artifacts (MVC, DB First, Design Patterns) & Code Repository |  | 1.5
| Master Pages/UI Theme - Integration |  | 2
| ER/Database Preperation - for Users, Roles n Security |  | 0.5
User Management & Security
| Users | Authorized Users allowed to interact with the system
| List View | User List View to List down all the System Users | 0.5
| Add/Edit View | User Add/Edit View to add new or update existing users | 1
User Login & Security
| Login Page | Login Page to authenticate valid users | 0.5
| Forgot Password Page | To change password using an authentication link | 0.5
| change Password Page | To change existing password | 0.5
| User Profile | Update Picture, Address etc | 1
| Rigts Managemnet |  | 3.5
|  | Total | 12.5

## Inventory Management
Analysis & DB Design
1 | Re Analysis with Team |  | 1.25
2 | DB Design |  | 1
Inventory Management
| Items |  | (Days)
| Items list Screen |  | 1
| Create new item |  | 1.25
| View Item |  | 0.5
| List of Item Variations Screen (SKUs) |  | 1
| Create new Item-specification (SKU) |  | 2
| View Item-variations (SKU) |  | 0.5
Warehouse
| Warehouse List |  | 1
| Create New Warehouse |  | 0.75
| View Warehouse Details |  | 0.5
RFI (Request for Item)
| Create new RFI (Request for Items) for Employee |  | 0.75
| RFI Add Item Popup |  | 1 | (First time)
| RFIs (Request for Items) list for Employee: |  | 1
| View RFI page (for employee) |  | 0.5
| RFIs list (for inventory manager) |  | 1
| RFI (needs response) details (for inventory manager) |  | 0.75
| RFI (responded to) details (for inventory manager) |  | 0.75
| RFI History pop-up (For inventory manager) |  | 0.5
IRF (Items Release Form)
| Create new Items Release Form (IRF) (for inventory manager) |  | 1
| RFI Add Item Popup |  | 0.5 | (repeated)
| IRFs list (for inventory manager) |  | 1
| View IRF (For inventory manager) |  | 0.5
| View IRF (For inventory manager) - Editing |  | 0.5
| IRFs list (For employee) |  | 0.5
| View IRF page (For employee) |  | 0.5
RIF (Returned Items Form)
| Create new Returned Items form (RIF) (For employee) |  | 1
| RIFs list (For employee) |  | 0.75
| View RIF (For employee) |  | 0.5
| RIFs list (For inventory manager) |  | 0.75
| View RIF (For inventory manager) |  | 0.5
DIF (Defected Items Forms)
| Create new Defected Items form (DIF) (For employee) |  | 1
| View DIF for employee |  | 0.5
| List of DIF for employee |  | 0.75
| View DIF for inventory manager |  | 0.5
| List of DIF for inventory manager |  | 0.75
TIR (Transfer Items Request)
| Create new Transfer Items Request (TIR) (for warehouse manager) |  | 1
| TIRs list (for warehouse manager) |  | 0.75
| View Sent TIR (for warehouse manager) |  | 0.5
| View Sent TIR (for warehouse manager) - Editing |  | 0.5
| Receive TIR (for warehouse manager) |  | 0.5
PO (Purchase Order)
| Create new Purchase Order (PO) (for warehouse manager) |  | 1
| Add item to the PO |  | 0.5
| List of PO |  | 0.75
| View PO (for warehouse manager) |  | 0.5
| Receive PO (for inventory manager) |  | 0.5
Physical Count
| List of Items (Physical Count) |  | 1.25
Vendors
| List of vendors |  | 0.75
| Create new vendor |  | 0.5
| View vendor |  | 0.5
| View vendor - Editing |  | 0.5
| Vendor list of transactions |  | 0.75
| Add a transaction |  | 0.5
Barcode Printer
| Barcode Printer |  | 1.25
| Item variation (SKU) Pop-up selector for barcode printing |  | 1
Deployment, Testing and Client Reworks
| Deployment | Current Module Deployment & Testing | 1
| Client ReWork |  | 1
| 2nd Deployment & Testing |  | 0.5
|  | Total | 44.5

## Financial Documents
Analysis & DB Design
1 | Re Analysis with Team |  | 1
2 | DB Design |  | 1
Financial Documents
Quotations
| From Control Panel: creating quotation |  | 1.75
| Add new item from quotation pop-up |  | 0.5
| Create new item from quotation pop-up |  | 0.5
| View Quotation (For employee) |  | 1
| For customer: respond to quotation |  | 0.5
| Payment method | (Payment Gateway R&D Required) | -
| For customer: list of quotations |  | 0.5
| For customer: View quotation |  | 0.5
Invoicing
| From Control Panel: creating invoice |  | 1.75
| Add new item from invoice pop-up |  | 0.5
| From control Panel: invoices screen |  | 0.5
| From Control Panel: View invoice |  | 0.5
| For customer: invoice |  | 0.5
| For customer: list of Invoices |  | 0.5
| For customer: view invoice |  | 0.5
Receipts
| From Control Panel: creating receipt |  | 1.75
| Add new item from Receipt pop-up |  | 0.5
| From Control Panel: receipts screen |  | 0.5
| From Control Panel: View receipt |  | 0.5
| For customer: receipt |  | 0.5
| For customer: list of receipts |  | 0.5
Deployment, Testing and Client Reworks
| Deployment | Current Module Deployment
| Testing at our end | Module & Integration Testing
Client ReWork
2nd Deployment
|  | Total | 16.25

## Website
Analysis & DB Design
1 | Re Analysis with Team |  | 1
2 | DB Design |  | 0.5
Website
Purchase History
| From Control Panel: customer purchase history |  | 0.75
| From control panel: customer RFQs |  | 0.75
Customers
| Form Control Panel: customer list |  | 0.5
| From Control Panel: customer profile |  | 0.5
Control Panel
| Form control panel: Adding/Updating Menu | Missing in Design | 1
| Menus - Front End |  | 0.5
| From control panel: home page | Slider, Main Divs, News & Articles, Partners | 3
| Home Page - Front End |  | 1.5
| From Control Panel: About us: content management system |  | 0.25
| About Us - Front End |  | 0.25
| From Control Panel: contact us |  | 0.75
| Contact Us - Front End |  | 0.5
| From Control Panel: Add new news or Article | List View, Add/Edit View, Details View | 1
| News & Articles - Front End |  | 1
| Catalogue |  | 0.75
| From Control Panel: Services screen |  | 0.5
| Services Screen - Front End |  | 0.5
| From Control Panel: Add products to website | Add Product, List View, Detail View | 1
| Product Specification - Front End | List of Products, Information & Specification Screens | 1
| From Control Panel: Products | Control “best sellers, featured, random, offers” slider | 0.5
| From Control Panel: Careers | Screen Missing | 1 | May vary upon screen design
| Careers - Front End | Screen Missing | 1
Others
| Search (Static + Dynamic Content) | Please elaborate details | - | Depends upon explanation of the Search Functionality
| Facebook Plugin Integration | Facebook Comments for Articles/News | 1.5 | R&D and Integration time
| Control Panel page for adding/editing/deleting Departments/Slider/Partners | Missing in Design |  | Time mentioned Above (Row # 18)
| Catalogue PDF Generation | Company Header/Footer on PDF + Products | 1.5
| E-Cart Screen Integration |  | 0.5
| Checkout Screen Integration |  | 0.5
Deployment, Testing and Client Reworks
| Deployment | Current Module Deployment & Testing | 1
| Client ReWork |  | 1
| 2nd Deployment & Testing |  | 1
|  | Total | 27

## Notification
Analysis & DB Design
1 | Re Analysis with Team |  | 0.25
2 | DB Design |  | 0
Notifications
Notifications
| Alert sent for each variation of the item |  | 0.5
| An alert if the total on-hand quantity reached a single level |  | 0.5
| Expiry date notification |  | 0.5
| RFI - Sending an alert to inventory manager |  | 0.5
| RFI - Alert when Edited |  | 0.5
| IRF - Alert to Employee mentioned and to the warehouse manager |  | 0.5
| Alert to warehouse manager to Update warehouse on accepting PO by inventory manager |  | 0.5
Deployment, Testing and Client Reworks
| Deployment | Current Module Deployment & Testing
Client ReWork
2nd Deployment & Testing
|  | Total | 3.75

## Customers & Invoices
Analysis & DB Design
1 | Re Analysis with Team |  | 1
2 | DB Design |  | 0.5
Customers
Customers
| List Vew | List View to list down all the customers in the system | 0 | Admin/PM
| Add Customer | Register new customers into the system | 0
| Profile/Details | View Customer Details, Projects, Invoices, Receits | 0 | Admin/PM
Customer Complaints
| List Vew | Customer and Admin can view complaints | 0 | Customer/Admin/PM
| Add/Edit View | Customer can launch new complaints | 0 | Customer
| Complaints Reply | Admin can view detail, can flag as read and add description/reply against it. And also can mark close | 0 | Admin
| Details | Complaints Detail Page for Customers where they can see the Admin's reply | 0 | Customer/Admin/PM
Invoice
| Add Invoice | Generate Customer Invoice | 1 | Admin
| Invoice List View | Customer Admin Can view their invoices | 0.75 | Customer/Admin
| Edit Invoice | Mark Invoice Paid UnPaid as well as date (Will be treated as Receipts) | 0.5 | Admin
Receipts
| Generate Receipts | Generate receipts against invoices | 0.75 | Customer
| Receipts List View | List down all the receipts against invoices | 0.75 | Admin/Customer
Orders
| Create New Order |  | 0.75 | Customer
| Order List View |  | 0.75 | Admin/PM
| Order Details |  | 0.75 | Customer
Quotation
| Create Quotation | Admin can create quotations | 1 | Admin
| Update Quotation | Admin can view/edit/update quotations | 0.75 | Admin
| Qutation Details | Customer can view quotation made by Admin | 0.75 | Customer
Deployment, Testing and Client Reworks
| Deployment | Current Module Deployment & Testing | 0.5
| Client ReWork |  | 0.5
| 2nd Deployment & Testing |  | 0.5
|  | Total | 10